Student ID - Please enter your UTA student ID number.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade. In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any
Leave blank initially (hint: Use the Delete key) Select "In Work" when you begin designing and coding this feature. Select "In Test" when this feature is fully coded and you are testing it. Select Finished ONLY when the feature works well and is READY TO
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab. For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that fe
Leave blank until task is begun. Select "In Work" when started (for long tasks only). Select Completed ONLY when this task is done. Select "Completed Day 1" if finished on the first day, and similarly for "Completed on Day 2" et. al.
## Product Backlog
Product Name:	C1325 Library Management System					Complete Fields in Green!!!
Team ID:					Sprints / Features Remaining at Start of Sprint

Name:	Emmanuel Gonzalez
Initials:	E.G.
Student ID:	1000905388

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	8		Total
Sprint 1 Left	7	1	1
Sprint 2 Left	7	0	2
Sprint 3 Left	7	0	3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
AP	1		1	In Work	Librarian	Add a publication	I can keep track of what is in the library
LP	2		1	In Work	Librarian	List all publications	I can find out what is in the library	This will also be needed for the next two features
CO	3		1	In Work	Librarian	Check out a publication	I can track who has borrowed each publication	Each publication will need to know if it is checked out or not
CI	4		1	In Work	Librarian	Check in a publication	I can tell when a publication is returned
HE	5		1	Finished in Sprint 1	Librarian	Get help	I can learn how to use the system
PA	6		1		Librarian	Add a patron	I can conveniently keep track of all patrons	This is the Bonus level
SP	7		1		Librarian	Select a patron when checking out a pub	I don't have to rekey recurring patron info	This is the Bonus level
CU	8		1		Librarian	Add custom info for each publication type	I can keep better track of library assets	This is the Extreme Bonus level

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Sep 21		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Sep 28		Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	6
Day 1 Left	6	0
Day 2 Left	6	0
Day 3 Left	6	0
Day 4 Left	6	0
Day 5 Left	6	0
Day 6 Left	6	0
Day 7 Left	6	0

	Feature ID		Description	Status	Notes
	AP		Create a Publication class with data and a constructor		Included a WRITTEN test with each constructor and method!
	AP		Add the to_string method to Publication
	AP		Add the is_checked_out method to Publication
	AP		Add the check_out method to Publication
	AP		Add the check_in method to Publication
	LP		--> Add additional tasks to complete the homework
	CO
	CI
	HE
	PA
	SP
	CU